## Cover
Risk No | Risk Descriptor | Untreated Score | Treated Score | Target Score | Key Comments | Appetite Level | Treated Score
1 | Workforce Wellbeing & Skills | 20 | 9 | 6 | The risk relating to workforce wellbeing and skills has increased, reflecting continued pressures on capacity, resilience and critical skills, particularly in digital. SCTS is managing this through planned action on digital skills, staff feedback from the corporate People Survey, new wellbeing resources, leadership development and staff recognition activity. The risk will remain under close review as these actions are delivered. | Low | ↑
2 | Health, Safety & Security | 20 | 6 | 6 | Health, safety and security risks are being effectively managed through dedicated oversight, incident reporting, approved policies, compliance checks and regular audits. During 2025, a total of 28 security audits were completed, with further assessments continuing across courtrooms and public areas. Site-specific issues are addressed through practical action, regular monitoring and maintenance. | Very Low | ↔
3 | Data Protection & Security | 25 | 12 | 6 | Protecting information remains a priority. We have made good progress in responding to the Information Commissioner’s Office audit recommendations and have strengthened oversight, reporting and monitoring arrangements. Some improvement actions remain ongoing, including work on logging, records management, training and wider assurance. We will continue to monitor progress closely to ensure these improvements are completed and embedded. | Low | ↔
4 | Organisational Resilience & Cyber Security | 25 | 12 | 6 | We have strengthened our organisational resilience and cyber security arrangements, including improved oversight, monitoring and threat intelligence, adoption of the National Cyber Security Centre’s Cyber Assessment Framework, and improved resilience arrangements for situations where normal systems are unavailable. Further work is still being implemented, tested and evidenced in practice. This area will remain under close review as improvements are completed and shown to be operating effectively. | Low | ↔
5 | Delivering Change & Service Reform | 20 | 12 | 9 | We are making good progress across our service reform programme, but delivery remains challenging due to the scale of change and continuing pressures in areas such as High Court business, civil digital reform, the Office of the Public Guardian, tribunal capacity and workforce planning. Work is underway to strengthen delivery, capacity and long-term planning. This includes reviewing leadership arrangements, improving how change is delivered, progressing the Office of the Public Guardian Strategic Case for Change, and supporting longer-term workforce planning. These actions are intended to improve delivery performance and support sustainable reform. | High | ↔
6 | Finance & Resources | 25 | 16 | 12 | Financial pressure remains a significant challenge for SCTS, affecting both core service delivery and the pace of reform. Although the latest forecast shows an overall underspend for 2025–26, underlying cost and investment pressures remain, particularly in areas such as building maintenance, digital modernisation and longer-term reform. The 2026–2029 Corporate Plan sets out important priorities for the coming years. Delivering these within annual budget settlements and the wider public finance context will require careful prioritisation, and some activity may need to be rephased or adjusted to remain affordable. | Medium | ↔
7 | Sustainable Services | 20 | 12 | 6 | Service sustainability pressures remain significant in a number of areas, including High Court solemn business, the Social Security Chamber and the Office of the Public Guardian. Actions are in place to manage these pressures, including the national implementation of Summary Case Management, additional staffing and performance monitoring in the Office of the Public Guardian, and targeted work on tribunal capacity and High Court planning. This area will remain under close review as these actions progress. | Medium | ↔
8 | Climate Change Compliance and Estate Preparedness | 20 | 9 | 9 | We continue to make progress in meeting our climate change duties and improving the sustainability of our estate. SCTS achieved Carbon Reduce certification for the second year running, with reported reductions in gas and electricity emissions of 18% and an overall emissions reduction of 10%. Work is also underway to support more sustainable travel, improve recycling, develop sustainability training and assess future clean heating requirements across the estate. Investment requirements and estate constraints will continue to be considered as this work progresses. | Medium | ↔

## Scoring
RISK SCORING KEY